## Project Data
Project Name | Engineering Knowledge Advisor
Online team meeting | https://fau.zoom-x.de/j/68492789151
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2026ws02-engineering-knowledge-advisor
GitHub feature board | https://github.com/orgs/amosproj/projects/110
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/114
Position of T-shirt logo | Upper Torso Right Small
Link to logo for black T-shirt | https://github.com/amosproj/amos2026ws02-engineering-knowledge-advisor/tree/main/Deliverables/sprint-01/team-logo.svg
Link to logo for white T-shirt | https://github.com/amosproj/amos2026ws02-engineering-knowledge-advisor/tree/main/Deliverables/sprint-01/team-logo.svg
Additional materials | https://github.com/amosproj/amos2026ws02-engineering-knowledge-advisor/tree/main/Deliverables/sprint-01/team-label.svg
We have a team label, if possible we would like this to be printed centered on the side of the upper arm,
Team maling list | oss-amos-proj2@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Medeiros da Cruz | Yan | yanmcruz | yan.medeiros.da.cruz@campus.tu-berlin.de
Pohl | Christian | ChristianJPohl | christian.j.pohl@fau.de
Wendlinger | Tom | tombln292 | tom.wendlinger@campus.tu-berlin.de
Drobischevskiy | Leonid | le-db | leonid.drobischevskiy@fau.de
Nadwornik | Jost | Jost-Na | nadwornik@campus.tu-berlin.de
Tenepo | Franklin | franktronics | wilson.f.tenepo@fau.de
Best | Lisabeth | PeppermintCoding123 | lisabeth.hasse@fau.de
Khan | Gulbaz | mgulbazilyas | gulbaz.khan@fau.de
Pasewaldt | Felix | felixp33 | felix.pasewaldt@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-10-14 | N/A | Yan | Everyone else | N/A | Lisabeth
2 | 2026-10-21 | Yan | Tom | Everyone else | Gulbaz | Lisabeth | Ask: should be weekly defined?
3 | 2026-10-28 | Tom | Yan | Everyone else |  | Lisabeth
4 | 2026-11-04 | Yan | Tom | Everyone else |  | Lisabeth
5 | 2026-11-11 | Tom | Yan | Everyone else |  | Lisabeth
6 | 2026-11-18 | Yan | Tom | Everyone else |  | Lisabeth | Yan not present
7 | 2026-11-25 | Tom | Yan | Everyone else |  | Lisabeth | Mid-term due
8 | 2026-12-02 | Yan | Tom | Everyone else |  | Lisabeth
9 | 2026-12-09 | Tom | Yan | Everyone else |  | Lisabeth
10 | 2026-12-16 | Yan | Tom | Everyone else |  | Lisabeth
11 | 2026-01-13 | Tom | Yan | Everyone else |  | Lisabeth
12 | 2026-01-20 | Yan | Tom | Everyone else |  | Lisabeth
13 | 2026-01-27 | Tom | Yan | Everyone else |  | Lisabeth
14 | 2026-02-03 | Yan | Tom | Everyone else |  | Lisabeth | Demo day!
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Team goal: Develop a high-quality, usable, and useful software solution for Bosch that addresses the company partner’s problem, while collaborating effectively, strengthening agile practices, and building industry connections.
Meeting norms | Meetings start at 12:30, and go on until 14:00. We start on time (let us know if there are any problems, if you won't attend or you will be late). Let us know in advance when you won't be able to attend, via whatsapp. We communicate outside of the team meetings on Discord (https://discord.gg/nmUEwuDyU). For every meeting there should be a moderator and time-keeper, to ensure the agenda is followed (scrum master/PO). There should be a meeting agenda prepared and sent beforehand. Meeting feedback will be prepared by the scrum master. Meeting summary will be prepared by the scrum master.
Working norms | We use pull requests and require a review. The main and dev branches is protected. We have a development branch. We do the release once a week (merge from dev to main). Code reviews for anything that goes into dev (require approval). Setup a CI pipeline. Autoformater. Do not squash commits; preferred is small commits for grading.
Coordination norms | POs will share the duties, week after week.
Communication norms | We communicate in English. We expect replies as fast as possible, preferrably within 24h.
Consideration norms | We respect each other ideas. We don't fill up the commits with AI slop: make sure you use AI responsibly.
Cont. improvement norms | Provide feedback on the team meeting. Whenever possible, share your best practices (on Discord or Team Meeting).
Rewards | Praise and appreciation upon good work! Share publicly or privately on Discord.
Sanctions | We don't think this can help team motivation
Signatures
Scrum Master | Lisabeth Best
Product owner | Yan Medeiros da Cruz
Product owner | Tom Wendlinger
Software developer | Gulbaz Khan
Software developer | Christian Pohl
Software developer | Leonid Drobischevskiy
Software developer | Franklin Tenepo
Software developer | Felix Pasewaldt
Software developer | Jost Nadwornik

## Product Goal
Product Vision | Project Mission
A knowledge database, LLM-readable and searchable, with an AI user interface that allows engineers both to capture their knowledge about existing products, linked to the respective CAD files and assembly groups, and to retrieve this knowledge during the design of new products. | Deliver an open-source prototype that lets Bosch engineers capture knowledge about existing products, linked to their CAD assembly groups, and retrieve it with AI during new designs.

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | Project Introduction and initial planning
2 | None
3 | None
4 | Optional
5 | Write your sprint goal here
6
7
8
9
10
11
12
13
14

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Velocity Tracking
Sprint # | Story Points Realized
1 | 0
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0

## Mid-Project Release plan
Sprint | Theme | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  |  | 0 | 0
Sprints
[5 empty] | Estimated burn-down |  | Real burn-down
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
... |  |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Theme | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  |  | 0 | 0
Sprints
[5 empty] | Estimated burn-down |  | Real burn-down
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
... |  |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment

## Planning Poker
Last Name | First Name | Value
Medeiros da Cruz | Yan | 0 | 0 | OK
Pohl | Christian | 0
Wendlinger | Tom | 0
Drobischevskiy | Leonid | 0
Nadwornik | Jost | 0 | 0 | No size
Tenepo | Franklin | 0 | 1 | Trivial size
Best | Lisabeth | 0 | 2 | Small size
Khan | Gulbaz | 0 | 3 | Medium size
Pasewaldt | Felix | 0 | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value